## README
OpenELIS Global — Quality Assurance Menu Roadmap
Roadmap + Working Tracker • Phase 0 Deliverable • 2026-04-23 • Casey Iiams-Hauser
Purpose
This workbook is the working tracker for the QA Menu consolidation effort. It captures the end-to-end plan, the four-pillar IA, the feature crosswalk (ideal vs. current), the six-sprint delivery roadmap, the flexible-roles permissions model, and dependencies/risks. Companion narrative lives in qa-menu-roadmap.md.
Objective
Give OpenELIS a coherent top-level Quality Assurance surface that a QA Officer, Lab Director, or visiting inspector can use to answer ISO 15189:2022's five quality questions within three clicks: (1) are runs in control (§7.3), (2) how did we perform in PT (§7.3), (3) are QIs on target (§8.8), (4) what NCEs are open and what are we doing (§8.7/§8.9), (5) are we accreditation-ready.
Sheet guide
Sheet | Purpose
README | Overview + navigation
Roadmap | Six-sprint delivery plan with gates
IA Proposal | Four-pillar Quality Assurance sidenav tree
Feature Crosswalk | Ideal vs. current state per feature, action column
Sprint Plan | Per-sprint deliverables and owners
Permissions | Flexible-roles permission keys + default role bundles
Dependencies & Risks | D# and R# items with mitigations
Decisions Log | Running record of locked scope and naming decisions
Deferred to v2+ | Items explicitly out of scope for v1
Non-goals for v1
No net-new lab features beyond the existing NCE/CAPA/EQA V2 design corpus. No multi-site rollup. No Accreditation Binder export. No time-boxable Inspector/Auditor credential. No QC/EQA/audit-trail backend rewrites.
Related artifacts
qa-menu-roadmap.md | Narrative companion to this workbook
admin-menu-redesign-roadmap.xlsx | Parallel initiative — coordinate Accreditation config placement
nce-report.md (v3.1) | NCE FRS including nce_capa + nce_effectiveness_review data model
nce-dashboard.md (v3.0) | Requires v4.0 revision — rehome NCE under QA → QMS
nce-analytics.md (v3.0) | Lives under QA → QMS → NCE Register → Analytics
nce-results-entry.md (v3.0) | Long-term target; current button is Phase-1 interim

## Roadmap
Sprint | Name | Objective | Key Deliverables | Dependencies | Est. Sessions | Verification Gate | Status
1 | IA Skeleton + NCE FRS v4.0 | Stand up the top-level QA sidenav, revise the NCE FRS to rehome NCE under QA → QMS, and register flexible-roles permission keys. | New top-level Quality Assurance sidenav group. QA Overview landing page (stub cards OK). NCE Dashboard FRS bumped v3.0 → v4.0 rehoming NCE under QA → QMS → NCE Register. Permission keys registered: qa.view.*, qa.manage.*, nce.*, eqa.*, audit.*, esig.*, accreditation.*. QA Officer default role pre-bundled. | Flexible-roles engine landing (D1). Admin menu redesign coordination (D3). | 2–3 | Casey sign-off on IA + FRS v4.0 + permission registry. | pending
2 | NCE/CAPA bedrock build | Build the NCE register, create/report flow, analytics, and reconcile the Results Entry spec. | NCE Register (list + filter + detail) per FRS v3.1. NCE Create/Report covering 11 trigger points. NCE Analytics (4 KPIs, 9 charts, 6 reports). Results Entry: keep live Report-NCE button; document v3.0 inline spec as long-term target; FRS flags current button as Phase-1 interim. | Sprint 1 IA merged. NCE FRS v4.0 locked. | 4–5 | End-to-end NCE lifecycle demo: open → investigate → CAPA → effectiveness review → close. | pending
3 | Rehomes + new QMS views | Rehome legacy QA-adjacent pages into the new IA and build the new QMS leaf views. | Rehome Westgard Rules + Run Review & Levey-Jennings under Statistical QC. Rehome Audit Trail under QMS (Admin cross-link preserved). Build CAPA Register view over existing data. Build Electronic Signature Log. Build Accreditation Status rollup (single-site). Rename EQA V2.3 'Lab Performance Dashboard' → 'EQA Lab Performance'. | Sprint 2 NCE data in place (feeds CAPA view). Admin menu redesign coordination. | 3–4 | Audit-trail rehome has no dead links; CAPA Register round-trips data with NCE Register. | pending
4 | Pillar-3 QI specs + dashboard | Close the Quality Indicators pillar — dashboard + three new indicator specs. | QI Dashboard (rollup tiles + deep-links). Rejection Rate FRS. Amendment Rate FRS. Critical Callback Compliance FRS. TAT Compliance deep-linked to existing report (no duplicate). | Three QI FRS outlines drafted (D4). | 3 | Each QI has a testable numerator/denominator and a target threshold. | pending
5 | EQA V2 MVP | Ship the EQA participant + oversight surfaces under the new QA menu. | My EQA. EQA Lab Performance (renamed). Follow-Up Queue. Analyst Competency. EQA Program Management rehome with eqa.provider-scoped visibility. | EQA V2 corpus renames applied (D5). | 4–5 | Participant flow (submit PT → see scorecard) + provider flow (create event → review submissions) both demo clean. | pending
6 | Results Entry NCE upgrade + v1 close-out | Swap the interim Report-NCE button for the full v3.0 inline-panel experience and close v1. | Swap Results Entry handler to render v3.0 inline panel (Sample Action radios, delta-check, NCE flag badge). QA Officer training materials refreshed. v1 acceptance tested against the five ISO 15189 quality questions. | Sprints 1–5 shipped. QA Officer training content ready. | 2 | All five ISO-15189 questions answerable in ≤3 clicks from QA Overview. | pending
7+ | v2 backlog (deferred) | Features deliberately deferred from v1. | QC Lot Management FRS + build. Accreditation Binder export. Time-boxable Inspector/Auditor credentials. Multi-site / multi-lab rollup. Document Control (§8.3). Equipment Management (§6.4). Risk Register (§8.5). Internal Audit Tracker (§8.9). | v1 close-out (Sprint 6). | TBD | Scope per-feature at start of v2 planning. | deferred
2-MVP | MVP KPI Rollup (closing FRS in spec sequence) | Ship a thin slice of the QI Dashboard early using only KPIs computable from existing data. Replaces the full version in place when Sprint 4 lands. | Three tiles: Rejection Rate, Amendment Rate, TAT Compliance. Three new REST wrappers (~8–11h). Detail placeholders + MVP banner. Reuses Sprint 4's full-version Carbon shell with conditional render. | Sprint 2 NCE/CAPA bedrock partially in flight (no hard dep). TAT compliance wrapper from Sprint 4 pulled forward. | 1–2 | Smoke test against fixture data; confirm Sprint-4 swap path works without URL or pref-state regression. | pending

## IA Proposal
IA v1.0 — Four-Pillar Quality Assurance Sidenav
Grounded in ISO 15189:2022 clauses. Top-level sibling of Orders, Validation, Reports, EQA, Admin. Uses submenus (not tabs) per sidenav convention.
Pillar | Sidenav Item | Clause | State | Notes
(root) | Quality Assurance | — | new | New top-level sidenav group. Gated by qa.view.* permissions.
QA Overview | QA Overview | §7.3–§8.9 | new | Pillar rollup landing page with 4 pillar tiles + 5 ISO 15189 quality questions.
Statistical QC | Run Review & Levey-Jennings | §7.3 | rehome | Currently under Validation. Move-only in Sprint 3; UI polish deferred.
Statistical QC | Westgard Rules | §7.3 | rehome | Currently under Validation/Analyzer. Move-only in Sprint 3.
Statistical QC | QC Lot Management | §7.3 | deferred | New spec deferred to v2 (Sprint 7+).
Statistical QC | Batch Workplan Reagent QC | §7.3 | exists | Cross-link only — lives in Workplan module.
Statistical QC | Analyzer Manual QC | §7.3 | exists | Cross-link only — lives in Analyzer module.
EQA (PT) | My EQA | §7.3 | rehome | Participant view. Currently EQA top-level.
EQA (PT) | EQA Oversight → EQA Lab Performance | §7.3 | rename | Renamed from 'Lab Performance Dashboard' (V2.3) to avoid collision with shipped Lab Management Dashboard.
EQA (PT) | EQA Oversight → Follow-Up Queue | §7.3 | spec'd | EQA V2 epic — build in Sprint 5.
EQA (PT) | EQA Oversight → Analyst Competency | §7.3 | spec'd | EQA V2 epic — build in Sprint 5.
EQA (PT) | EQA Program Management | §7.3 | rehome | Provider-only (eqa.provider). Currently EQA top-level.
Quality Indicators | QI Dashboard | §8.8 | new | Rollup of four QIs. Build in Sprint 4.
Quality Indicators | TAT Compliance | §8.8 | deep-link | Deep-link to existing TAT report — do not duplicate.
Quality Indicators | Rejection Rate | §8.8 | new | New FRS in Sprint 4.
Quality Indicators | Amendment Rate | §8.8 | new | New FRS in Sprint 4.
Quality Indicators | Critical Callback Compliance | §8.8 | new | New FRS in Sprint 4.
QMS & Improvement | NCE Register | §8.7 | rehome | FRS v4.0 rehomes from top-level to here (Sprint 1 revision).
QMS & Improvement | CAPA Register | §8.9 | new | View over existing nce_capa + nce_effectiveness_review tables. No new entity.
QMS & Improvement | Accreditation Status | §8.x | new | Rollup only in v1. Binder export deferred.
QMS & Improvement | Audit Trail | §8.4 | rehome | From Admin. Admin-side cross-link preserved so muscle memory still works.
QMS & Improvement | Electronic Signature Log | §8.4 | new | New log view in Sprint 3.
Admin (cross-link) | QI Configuration | §8.8 | new | New admin leaf page configuring all four Pillar-3 QIs (enable/disable, thresholds, per-QI behavior toggles). Cross-linked from QA → Quality Indicators → QI Dashboard header utility.

## Feature Crosswalk
ID | Pillar | Feature | Exists Today? | Current Location | Action | Sprint | Notes
F01 | Statistical QC | Levey-Jennings charts | Yes | Under Validation | Rehome | 3 | Move-only in Sprint 3.
F02 | Statistical QC | Westgard multi-rule config | Yes | Validation/Analyzer | Rehome | 3 | Move-only in Sprint 3.
F03 | Statistical QC | QC Lot Management (target/SD governance) | No | — | New | 7+ | Deferred to v2.
F04 | Statistical QC | Batch Workplan Reagent QC | Yes | Workplan module | Cross-link | 3 | Stays in Workplan; cross-link from QA menu.
F05 | Statistical QC | Analyzer Manual QC | Yes | Analyzer module | Cross-link | 3 | Stays in Analyzer; cross-link from QA menu.
F06 | EQA (PT) | My EQA (participant view) | Yes | EQA top-level | Rehome | 5 | Build with EQA V2 MVP.
F07 | EQA (PT) | EQA Lab Performance (renamed) | Spec'd | EQA V2.3 | Rename + Build | 5 | Renamed from 'Lab Performance Dashboard'.
F08 | EQA (PT) | Follow-Up Queue | Spec'd | EQA V2 | Build | 5 | EQA V2 epic.
F09 | EQA (PT) | Analyst Competency | Spec'd | EQA V2 | Build | 5 | EQA V2 epic.
F10 | EQA (PT) | EQA Program Management | Yes | EQA top-level | Rehome | 5 | Provider-only.
F11 | Quality Indicators | QI Dashboard | No | — | New | 4 | Outline drafted (qi-dashboard-outline.md). Build in Sprint 4. Visibility logic respects QI Configuration enable/disable per DEC19.
F12 | Quality Indicators | TAT Compliance | Yes (report) | Reports | Deep-link | 4 | No duplication of TAT logic.
F13 | Quality Indicators | Rejection Rate | No | — | New | 4 | Outline drafted (qi-rejection-rate-outline.md). Spec + build in Sprint 4.
F14 | Quality Indicators | Amendment Rate | No | — | New | 4 | Outline drafted (qi-amendment-rate-outline.md). Spec + build in Sprint 4.
F15 | Quality Indicators | Critical Callback Compliance | No | — | New | 4 | Outline drafted (qi-critical-callback-compliance-outline.md). Spec + build in Sprint 4. Likely Sprint 3 schema audit + Sprint 4 migration if callback log lacks read-back fields.
F16 | QMS | NCE Register | Spec'd (v3.1) | Top-level (v3.0) — needs v4.0 revision | Rehome | 1+2 | v4.0 revision in Sprint 1; build in Sprint 2.
F17 | QMS | CAPA Register | Data model exists | nce_capa + nce_effectiveness_review tables (v3.1) | New view | 3 | Outline drafted (capa-register-outline.md). View over existing nce_capa data — no new entity per DEC05. Build in Sprint 3.
F18 | QMS | Accreditation Status rollup | No | — | New | 3 | Outline drafted (accreditation-status-outline.md). Single-site v1 per DEC03; binder PDF deferred to v2 per DEC09. Build in Sprint 3.
F19 | QMS | Audit Trail | Yes | Admin menu | Rehome | 3 | Cross-link preserved from Admin.
F20 | QMS | Electronic Signature Log | No | — | New | 3 | Outline drafted (electronic-signature-log-outline.md). UNION over 4 existing audit tables. Build in Sprint 3.
F21 | Results Entry | Report NCE button (interim) | Yes (live) | Results Entry page | Document as Phase-1 | 2 | Keep live. FRS flags as Phase-1 interim.
F22 | Results Entry | v3.0 inline NCE panel (target) | Spec'd | nce-results-entry.md v3.0 | Swap handler | 6 | Sample Action radios + delta-check + NCE flag badge.
F23 | Quality Indicators (Admin) | QI Configuration admin page | No | — | New | 4 | Per-lab enable/disable + per-QI threshold/behavior config. Outline drafted (qi-configuration-outline.md). Build in Sprint 4.
F24 | QA (root) | QA Overview landing page | No | — | New | 1 | Default landing for the Quality Assurance menu. Outline drafted (qa-overview-outline.md). Build in Sprint 1.
F25 | Quality Indicators (MVP) | MVP QI Dashboard (3-tile early ship) | No | — | New | 2-MVP | Outline drafted (qa-mvp-kpi-rollup-outline.md). Ships 3 KPI tiles using existing data + small wrappers. Replaced in place by full Sprint 4 dashboard.

## Sprint Plan
Sprint | Workstream | Deliverable | Type | Links / Source | Acceptance | Status
1 | IA | Top-level Quality Assurance sidenav group added | Build | — | Renders as a sibling of Admin/Orders/Validation/Reports/EQA. QA Overview landing page loads without errors. | pending
1 | IA | QA Overview landing page (stub cards OK) | Build | — | Four pillar tiles present; each deep-links to its pillar landing. | pending
1 | Spec | NCE Dashboard FRS v3.0 → v4.0 revision | Spec | nce-dashboard.md | Top-level NCE menu entry removed; NCE rehomed under QA → QMS → NCE Register. | pending
1 | RBAC | Register flexible-roles permission keys | Build | project_flexible_roles.md | qa.view.*, qa.manage.*, nce.*, eqa.*, audit.*, esig.*, accreditation.* all appear in permission registry. | pending
1 | RBAC | QA Officer default role pre-bundled | Build | — | New install ships with QA Officer role containing the correct permission bundle. | pending
2 | Build | NCE Register (list + filter + detail) | Build | nce-report.md v3.1 | CRUD against nce_event + linked tables; filters for status, severity, category. | pending
2 | Build | NCE Create/Report flow (11 triggers) | Build | nce-report.md v3.1 | All 11 trigger points route to correct NCE template with context preloaded. | pending
2 | Build | NCE Analytics page | Build | nce-analytics.md v3.0 | 4 KPIs + 9 charts + 6 reports render against live NCE data. | pending
2 | Reconcile | Results Entry: document button as Phase-1 | Spec | nce-results-entry.md v3.0 | FRS explicitly notes current button as interim; v3.0 inline panel as long-term target. | pending
3 | Rehome | Westgard Rules rehomed | Move | — | Sidenav path updated; old path redirects; no dead links. | pending
3 | Rehome | Run Review & Levey-Jennings rehomed | Move | — | Sidenav path updated; old path redirects. | pending
3 | Rehome | Audit Trail rehomed to QMS (Admin cross-link kept) | Move | — | Both paths resolve; analytics not double-counted. | pending
3 | Build | CAPA Register view | Build | nce-report.md v3.1 | View renders all nce_capa records with filter/sort; round-trips to NCE detail. | pending
3 | Build | Electronic Signature Log | Build | — | Filterable log of all e-signature events with actor + artifact link. | pending
3 | Build | Accreditation Status rollup | Build | — | Single-site rollup tiles for CAP/ISO 15189 readiness indicators. | pending
3 | Rename | EQA V2.3 'Lab Performance Dashboard' → 'EQA Lab Performance' | Rename | EQA V2 corpus | All references updated; i18n keys migrated. | pending
4 | Spec | Rejection Rate FRS | Spec | — | Numerator/denominator/threshold/data source locked. | pending
4 | Spec | Amendment Rate FRS | Spec | — | Numerator/denominator/threshold/data source locked. | pending
4 | Spec | Critical Callback Compliance FRS | Spec | — | Numerator/denominator/threshold/data source locked. | pending
4 | Build | QI Dashboard with 4 QI tiles + TAT deep-link | Build | — | Each tile shows current value, target, trend arrow. | pending
5 | Build | My EQA | Build | EQA V2 MVP | Participant can see open events, submit results, view scorecard. | pending
5 | Build | EQA Lab Performance | Build | EQA V2 MVP | Cumulative performance across cycles/schemes; sigma where available. | pending
5 | Build | Follow-Up Queue | Build | EQA V2 MVP | Failed-cycle actions tracked to resolution. | pending
5 | Build | Analyst Competency | Build | EQA V2 MVP | Per-analyst competency per test; auto-suspension triggers on failure. | pending
5 | Rehome | EQA Program Management (provider-only) | Move | — | Visible only to eqa.provider permission. | pending
6 | Build | Swap Results Entry handler to v3.0 inline panel | Build | nce-results-entry.md v3.0 | Sample Action radios + auto-delta-check + NCE flag badge live; button becomes panel trigger. | pending
6 | Docs | QA Officer training materials refreshed | Docs | — | Training covers the swap; no user confusion tickets post-swap. | pending
6 | Verify | v1 acceptance — five ISO 15189 quality questions | Verify | — | Each of the five questions answerable in ≤3 clicks from QA Overview. | pending
3 | Spec | Rejection Rate FRS outline drafted | Spec | qi-rejection-rate-outline.md | Outline covers numerator/denominator/data sources/UI sketch/open Qs. Full FRS in Sprint 4. | outline
3 | Spec | Amendment Rate FRS outline drafted | Spec | qi-amendment-rate-outline.md | Outline covers numerator/denominator/data sources/UI sketch/open Qs. Full FRS in Sprint 4. | outline
3 | Spec | Critical Callback Compliance FRS outline drafted | Spec | qi-critical-callback-compliance-outline.md | Outline covers numerator/denominator/data sources/UI sketch/open Qs. Full FRS in Sprint 4. | outline
4 | Spec | NCE Report FRS v3.2 sub-revision (Critical Callback Failure trigger) | Spec | nce-report.md | Add Post-Analytical / Critical Callback Failure subcategory + new trigger. Required by the Critical Callback QI build. | pending
3 | Inventory | Critical-result callback log schema audit | Inventory | — | Confirm whether existing log captures caller, recipient, read-back confirmation, and ack time. If not, plan a Sprint 4 migration. | pending
3 | Spec | Sprint 4 pre-scoping doc (16 open Qs) | Spec | qi-sprint4-prescoping.md | Resolve open questions across the three QI outlines before Sprint 4 cold-starts. | outline
3 | Spec | QI Configuration admin page outline drafted | Spec | qi-configuration-outline.md | New admin page enabling/disabling each Pillar-3 QI per lab + threshold/behavior config. Default state per QI documented. Outline only; full FRS in Sprint 4. | outline
4 | Build | Build Admin → QI Configuration page | Build | qi-configuration-outline.md | Enable/disable toggle per QI. Per-QI threshold panel. Disable cascade behavior. Audit log routes to QMS Audit Trail. | pending
4 | Build | Disable cascade implementation in QI Dashboard + Alerts + NCE auto-gen | Build | qi-configuration-outline.md §4.4 | When a QI is disabled: tile removed, detail 404 with redirect, alerts suppressed, NCE auto-gen suppressed (Critical Callback Failure subcategory hidden), background recompute skips, history preserved. | pending
4 | Build | Per-test threshold override table on Rejection Rate config panel | Build | qi-configuration-outline.md §4.2 | Add/edit/remove rows for tests with overrides. Override falls back to category default when not set. Audit log writes diff per row change. | pending
3 | Spec | QI Dashboard outline drafted | Spec | qi-dashboard-outline.md | Pillar-3 rollup landing page. Four QI tiles, header strip, visibility logic tied to QI Configuration, empty state. Roll-up source for QA Overview's Quality Indicators tile. | outline
4 | Build | Build QI Dashboard landing page | Build | qi-dashboard-outline.md | Tile grid + header strip + empty state + reporting-window selector + per-user persistence. TAT tile deep-links to existing report. | pending
4 | Build | Add /rest/reports/tat/compliance wrapper endpoint | Build | TATReportRestController.java + new TATComplianceResponse.java | Reuses TATReportServiceImpl summary path; applies threshold arithmetic to histogram. Returns {compliancePercentage, passCount, failCount, threshold, asOf}. Inherits existing /summary security. | pending
0 | Spec | QA Overview landing page outline drafted | Spec | qa-overview-outline.md | Five-question strip + 4 pillar tiles, roll-up status from each pillar. Default landing for the QA menu. Sprint 1 build target. | outline
1 | Build | Build QA Overview landing page | Build | qa-overview-outline.md | Five-question strip, 4 pillar tiles, worst-of aggregation per pillar, last-recomputed timestamp, refresh button, empty/degraded states. | pending
1 | Inventory | Audit four pillar rollup endpoints (QC / EQA / QI / NCE) | Inventory | qa-overview-outline.md §11 | Confirm which exist as JSON/REST. Pattern follows the TAT compliance wrapper: any missing rollup gets a thin wrapper added in Sprint 1 alongside the QA Overview build. | pending
1 | Build | Add /rest/qc/dashboard/sections wrapper for QA Overview QC tile | Build | QCRestController.java + new QCSectionsSummary DTO | Per-section worst-of status + counts. Reuses QCDashboardService.computeDateRange() for window logic. Flag-and-proceed cross-team review. | pending
5 | Build | Add /rest/eqa/cycles/latest-performance wrapper for QA Overview EQA tile | Build | EQAOrdersRestController.java (or new EQACyclesRestController.java) + cycle-summary DTO | Returns most-recent-graded cycle per scheme. Worst-of computed client-side from the response. Skips ungraded in-flight cycles per DEC27. Pending EQA V2 build (Sprint 5); EQA V2 introduces the cycle/scheme model this wrapper queries. | pending
3 | Spec | MVP KPI Rollup outline drafted | Spec | qa-mvp-kpi-rollup-outline.md | Closing FRS in the spec sequence. 3-tile MVP + Sprint-4 transition behavior. | outline
2-MVP | Build | Add /rest/qi/rejection-rate wrapper | Build | new RejectionRateRestController.java + DTO | Joins sample_test_order to nce_event via nce_sample_link/nce_result_link. Returns rate, numerator, denominator, per-test-category breakdown. ~3-4h. | pending
2-MVP | Build | Add /rest/qi/amendment-rate wrapper | Build | new AmendmentRateRestController.java + DTO | Reads result_history for post-validation status diffs. Counts changes-that-alter-clinical-interpretation per AR-Q1. Returns rate, numerator, denominator, per-test-category breakdown. ~3-4h. | pending
2-MVP | Build | TAT compliance wrapper pulled forward from Sprint 4 | Build | TATReportRestController.java + new TATComplianceResponse | Same wrapper specced for full Sprint 4 (DEC23). Pulled forward into MVP fast-follow. No double-build. | pending
2-MVP | Build | Build MVP QI Dashboard frontend (3 tiles + detail placeholders) | Build | qa-mvp-kpi-rollup-outline.md | Carbon dashboard shell with 3 tiles. Detail-page placeholders = filterable tables with NCE links. MVP banner at top. Reuses Sprint 4 Carbon components with conditional rendering for omitted Sprint-4 elements. | pending
2-MVP | Build | NCE Pulse tile — client-side filter on existing /rest/nce/dashboard | Build | qa-mvp-kpi-rollup-outline.md §3 + §10 | Filter existing payload: severity=Critical AND status IN (open, acknowledged) for critical count; walk nce_capa for due_date < now() AND status != completed for overdue count. Drill-through deep-links to NCE Register filtered to same set. ~1h frontend; no backend. | pending
3 | Spec | CAPA Register outline drafted | Spec | capa-register-outline.md | View over existing nce_capa + nce_effectiveness_review (no new entity per DEC05). 4 summary tiles, filter/sort, drill-through to parent NCE, bulk reassign + bulk mark-complete. | outline
3 | Spec | Electronic Signature Log outline drafted | Spec | electronic-signature-log-outline.md | Filterable read-only log over 4 existing audit-event sources (result_history, nce_audit_log, sample_audit_log, qc_audit_log). CSV + PDF export. 9 v1 artifact types. Schema audit needed in Sprint 3 inventory. | outline
3 | Spec | Accreditation Status outline drafted | Spec | accreditation-status-outline.md | Single-site rollup against ISO 15189:2022 + CAP COM + CAP GEN. Per-section grid, outstanding-items list, evidence drill-through. Binder PDF deferred to v2 per DEC09. Heaviest of the three Sprint 3 outlines (~12-16h endpoint work). | outline
3 | Build | Build CAPA Register page | Build | capa-register-outline.md | List + filter + summary tiles + row expansion + bulk actions. New endpoint /rest/nce/capa (~3-4h). Drill-through to parent NCE. | pending
3 | Build | Build Electronic Signature Log page | Build | electronic-signature-log-outline.md | Single query against existing electronic_signature table (filtered by record_type). Joins to artifact tables for display. CSV + PDF export gated on esig.export. Endpoint effort ~2-3h (down from initial 6-8h estimate after code audit revealed unified table). Optional small migration adds prior_state/new_state columns for row-expansion state diff. | pending
3 | Build | Build Accreditation Status page | Build | accreditation-status-outline.md | REDIRECTED v0.2 model: lab-attested accreditation registry (CRUD on accreditation_record) + QA-evidence-at-a-glance tiles linking to existing surfaces. Single new accreditation_record table + small internal_audit_review_log table. Endpoint effort ~6-8h (down from initial 12-16h). No clause mapping, no evidence-stale logic, no Outstanding/Met state. | pending
3 | Inventory | Audit 4 audit-table schemas (result_history, nce_audit_log, sample_audit_log, qc_audit_log) | Inventory | electronic-signature-log-outline.md §11 | Confirm all four capture actor_user_id, signed_at, reason in compatible shapes. Migration if not. | pending
3 | Inventory | Audit existing IP / user-agent capture in audit tables | Inventory | electronic-signature-log-outline.md §11 | Required for 21 CFR Part 11 PDF export quality. If missing, add small migration in Sprint 3. | pending
3 | Spec | (SUPERSEDED) Draft default ISO 15189 + CAP COM/GEN evidence mapping | Spec | accreditation-status-outline.md §5 | Superseded by Accreditation Status redirection (DEC48). No clause mapping in v1. | superseded

## Permissions
Flexible-Roles Permissions Model
Permissions are atomic. Roles are bundles. QA Officer ships as the only new default role. Lab Director + Inspector/Auditor are composable bundles (recipes), not shipped roles.
Permission Key | Grants Access To | Default Role: QA Officer | Bundle: Lab Director / Inspector
qa.view.overview | Read QA Overview landing | Yes | Both
qa.view.qc | Read Statistical QC pillar | Yes | Both
qa.manage.qc | Manage QC rules / lots / review | No | Director only
qa.view.eqa | Read EQA pillar (participant views) | Yes | Both
qa.manage.eqa | Manage EQA oversight (non-provider) | Yes | Director only
qa.view.qi | Read Quality Indicators pillar | Yes | Both
qa.manage.qi | Configure QI thresholds | Yes | Director only
qa.view.qms | Read QMS & Improvement pillar | Yes | Both
qa.manage.qms | Manage QMS artifacts (non-signing) | Yes | Director only
nce.view.own | View NCEs assigned to me | Yes | Both
nce.view.all | View all NCEs | Yes | Both
nce.acknowledge | Acknowledge an NCE | Yes | Director only
nce.investigate | Perform investigation steps | Yes | Director only
nce.capa.manage | Author/update CAPA | Yes | Director only
nce.assign | Reassign NCE ownership | Yes | Director only
nce.effectiveness.review | Perform effectiveness review | Yes | Director only
nce.batch | Batch-manage NCEs | Yes | Director only
eqa.provider | Manage EQA programs as provider | No | Provider only
eqa.oversight | Oversight of EQA participants (non-provider) | Yes | Director only
eqa.participant | Submit EQA results as participant | No | Participant analysts
audit.view | View audit trail | Yes | Both
audit.export | Export audit trail | No | Director only
esig.view | View e-signature log | Yes | Both
esig.export | Export e-signature log | No | Director only
accreditation.view | View Accreditation Status | Yes | Both
accreditation.manage | Edit accreditation metadata | No | Director only

## Dependencies & Risks
ID | Type | Item | Impact | Mitigation | Owner | Status
D1 | Dependency | Flexible-roles engine must land before Sprint 1 closes | Blocks QA Officer default role + permission keys | Sprint 1 can ship with feature-flagged permission checks; role bundling slides to Sprint 2 if engine slips. | Engineering lead | pending
D2 | Dependency | NCE Dashboard FRS v4.0 revision | Blocks Sprint 1 IA lock | Bundled into Sprint 1 scope so it cannot be forgotten. | Casey | pending
D3 | Dependency | Admin Menu IA redesign parallel initiative | Accreditation config placement could drift | Coordinate Phase 3 of admin-menu-redesign with Sprint 3 of this roadmap; lock Accreditation config path jointly. | Casey | pending
D4 | Dependency | Three Pillar-3 QI specs must be written | Blocks Sprint 4 build | Specs owned in Sprint 4 (write + build in same sprint); pre-work in Sprint 3. | Casey | pending
D5 | Dependency | EQA V2.3 'Lab Performance Dashboard' rename | Downstream doc drift | Rename locked in Sprint 3; update all references in EQA V2 corpus before Sprint 5 build. | Casey | pending
R1 | Risk | Button-vs-inline-form Results Entry reconciliation | Analyst workflow change mid-rollout | Keep button live through Sprint 2–5; swap handler in Sprint 6 after QA Officer training materials land. | Casey | pending
R2 | Risk | Audit Trail rehome breaks Admin muscle memory | Admin users lose the path they know | Preserve the Admin-side link to Audit Trail so old muscle memory still works. | Casey | pending
R3 | Risk | Single-site scope omits ministry networks | Multi-lab customers get v1 with no comparison view | Document explicitly in release notes; multi-site stays in v2 backlog. | Casey | pending
R4 | Risk | 'QA Overview' stubbed pillar tiles look empty early | Perception that feature is undercooked | Stub tiles show 'Pillar under construction — see roadmap' with deep link, not blank cards. | Casey | pending
D6 | Dependency | NCE Report FRS v3.2 sub-revision must land before Critical Callback QI build | Without the new Critical Callback Failure NCE subcategory + trigger, the QI cannot drill through to NCEs. | Bundle the v3.2 sub-revision into Sprint 4 ahead of the Critical Callback build. | Casey | pending
D7 | Dependency | Critical-result callback log schema may need extension | If the existing log doesn't capture caller, recipient, read-back, and ack time, the Critical Callback QI cannot compute compliance. | Sprint 3 inventory audits the schema. If extension is needed, queue a Sprint 4 migration ahead of QI build. | Engineering lead | pending
R5 | Risk | 16 open questions across the three QI outlines | Sprint 4 cold-starts with unresolved scope decisions. | Pre-scoping doc in Sprint 3 walks through all 16 with recommended defaults; resolve with Casey before Sprint 4 kickoff. | Casey | in progress
R6 | Risk | Disable cascade has many surfaces to coordinate | When a QI is disabled, tile/detail/alerts/NCE auto-gen/recompute all need to consistently respect the toggle. Easy to miss a surface. | Single feature flag read by all surfaces. Acceptance test: toggle Critical Callback off → verify tile gone, detail 404, no new alerts, no new NCEs of that subcategory, no recompute load. | Engineering lead | pending
D8 | Dependency | TAT compliance wrapper endpoint must land before QI Dashboard build | QI Dashboard TAT tile cannot render without compliance % data. | Both are Sprint 4 deliverables; wrapper is small (controller + DTO only). Sequence wrapper first within the sprint. | Engineering lead | pending
D9 | Dependency | QC wrapper endpoint must land before QA Overview build (Sprint 1) | QA Overview QC tile cannot render without the section-level wrapper. EQA tile is deferred — renders gray 'pending' from Sprint 1 to Sprint 5 (until EQA V2 ships). NCE tile uses existing endpoint; QI tile lives in Sprint 4. | QC wrapper is small (~2-3h). Sequence within Sprint 1: wrapper first, then QA Overview build. EQA wrapper rolls into Sprint 5 alongside EQA V2 MVP. | Engineering lead | pending
D10 | Dependency | EQA V2 build (Sprint 5) gates the QA Overview EQA tile | EQA V2 introduces the cycle/scheme model that the latest-performance wrapper queries. Until V2 ships, the QA Overview EQA tile and Q2 of the five-question strip render gray 'pending.' | QA Overview ships in Sprint 1 with documented gray-state behavior for EQA. Sprint 5 closes the loop by building V2 and the wrapper together; QA Overview EQA tile lights up automatically when the wrapper endpoint goes live. | Casey | pending

## Decisions Log
ID | Date | Decision | Context / Rationale | Sprint | Made By | Supersedes
DEC01 | 2026-04-23 | New top-level 'Quality Assurance' sidenav, not just a landing page linking out | A landing page that links out would preserve the fragmentation we're trying to fix. Top-level group forces the IA. | 0 | Casey + Claude
DEC02 | 2026-04-23 | Four-pillar IA: Statistical QC / EQA-PT / Quality Indicators / QMS & Improvement | Mirrors ISO 15189:2022 clause structure (§7.3, §7.3, §8.8, §8.7+§8.9). Maps cleanly to CAP checklist sections. | 0 | Casey + Claude
DEC03 | 2026-04-23 | Single-site scope for v1 (no multi-lab rollup) | Keeps scope tight; multi-site is a separate initiative. | 0 | Casey
DEC04 | 2026-04-23 | Audit Trail moves from Admin to QMS (with cross-link preserved) | ISO 15189 treats audit trail as a QMS artifact; preserving Admin cross-link protects muscle memory. | 0 | Casey + Claude
DEC05 | 2026-04-23 | CAPA is not net-new — data model already in NCE FRS v3.1 | nce_capa + nce_effectiveness_review tables already specified. CAPA Register becomes a standalone view over existing data. | 0 | Claude
DEC06 | 2026-04-23 | NCE FRS needs v4.0 revision to rehome under QA → QMS → NCE Register | v3.0 specifies NCE as top-level menu — conflicts with DEC01. | 1 | Casey + Claude | nce-dashboard.md v3.0 top-level menu placement
DEC07 | 2026-04-23 | Rename EQA V2.3 'Lab Performance Dashboard' to 'EQA Lab Performance' | Avoids collision with shipped Lab Management Dashboard; 'EQA' prefix scopes it unambiguously. | 3 | Casey + Claude | EQA V2.3 spec name 'Lab Performance Dashboard'
DEC08 | 2026-04-23 | Results Entry: keep current button as Phase-1 interim; v3.0 inline panel is long-term target | v3.0 adds Sample Action at point-of-capture, auto-delta-check, mandatory trigger #4, row-level NCE flag badge — ISO 15189 §7.3/§8.7 value the button cannot provide. Swap in Sprint 6. | 2 | Casey + Claude
DEC09 | 2026-04-23 | Accreditation Binder export deferred to v2 | Out of scope for v1; single-site rollup ships in Sprint 3 without export. | 0 | Casey
DEC10 | 2026-04-23 | Time-boxable Inspector/Auditor credential deferred to v2 | Net-new engine capability; treat as a flexible-roles enhancement, not a role definition. | 0 | Casey
DEC11 | 2026-04-23 | Flexible-roles model — ship QA Officer as new default role only | Permissions are the atomic unit. Lab Director and Inspector/Auditor documented as composable bundles (recipes), not shipped roles. | 1 | Casey + Claude | Earlier proposal to ship three new default roles
DEC12 | 2026-04-23 | Sprint 1 (IA skeleton) sequenced before Sprint 2 (NCE/CAPA bedrock) | Skeleton-before-bedrock: every subsequent sprint needs a stable container to land into. | 1 | Casey + Claude
DEC13 | 2026-04-23 | Three QI outline FRSes drafted ahead of Sprint 4 | Avoids cold-start in Sprint 4. Each outline covers formula, data sources, thresholds, UI sketch, NCE linkage, permissions, acceptance criteria, open questions, and i18n tags. | 3 | Casey + Claude
DEC14 | 2026-04-23 | NCE Report FRS will need a v3.2 sub-revision in Sprint 4 | Critical Callback Compliance QI requires a new Post-Analytical / Critical Callback Failure NCE subcategory + trigger; no current trigger covers it. | 4 | Casey + Claude
DEC15 | 2026-04-23 | Sprint 3 will audit the critical-result callback log schema | If the schema doesn't already capture caller, recipient, read-back confirmation, and acknowledgment time, Sprint 4 starts with a small migration. Confirm in inventory. | 3 | Casey + Claude
DEC16 | 2026-04-23 | Rejection Rate scope locked across 5 questions | RR-Q1: hybrid recompute (live ≤ 7d, nightly > 7d). RR-Q2: partial rejection = 1.0. RR-Q3: out of scope (DEC03). RR-Q4 (REVISED 2026-04-23): unit of measurement is test ORDER, not sample; threshold table keyed on test category with per-test override. Specimen type demoted to secondary filter. RR-Q5: count all in headline. | 3 | Casey + Claude
DEC17 | 2026-04-23 | Amendment Rate scope locked across 5 questions | AR-Q1: count only changes that alter clinical interpretation. AR-Q2: addenda count as 1, tagged. AR-Q3: count auto-reruns; toggle defaulting OFF. AR-Q4: no headline cutoff; track elapsed time. AR-Q5: raw rate v1, severity weighting v2. | 3 | Casey + Claude
DEC18 | 2026-04-23 | Critical Callback Compliance scope locked across 7 questions | CC-Q1: schema audit in Sprint 3. CC-Q2: 'unable to reach' non-compliant by default. CC-Q3: wall-clock target. CC-Q4: auto-paging deferred. CC-Q5: critical-value list inventory in Sprint 3. CC-Q6: overall target only. CC-Q7: this QI is OPTIONAL — admin-configurable per lab. | 3 | Casey
DEC19 | 2026-04-23 | Pillar-3 QIs are admin-configurable on/off per lab | Each QI has an enable/disable toggle in a new Admin → QI Configuration page. TAT/Rejection/Amendment default ON (universally relevant). Critical Callback defaults OFF (reference labs without direct clinical communication don't need it). Disable cascade: tile removed, detail 404, alerts suppressed, NCE auto-generation suppressed where applicable, history preserved. | 4 | Casey
DEC20 | 2026-04-23 | RR-Q4 revised: Rejection Rate uses test-order as unit, not sample | Earlier RR-Q4 answer (specimen type only) overridden. Test-order unit attributes rejections to specific tests, aligns with IFCC/CAP per-test reference rates, and supports per-test threshold overrides for high-impact tests (critical INR, beta-hCG). Formula change: numerator/denominator both at test-order level. A full-sample rejection contributes N (one per test ordered); partial rejections contribute per affected test. | 3 | Casey | DEC16 RR-Q4 (specimen type only)
DEC21 | 2026-04-23 | QI Configuration Rejection Rate panel adds per-test override table | Per-test-category default thresholds with optional per-test row-level overrides for tests where rejection has higher clinical impact. Empty override table by default; category default applies. | 4 | Casey + Claude
DEC22 | 2026-04-23 | QI Dashboard is a thin rollup page; substance lives in per-QI outlines | Page only owns: tile layout, visibility tied to QI Configuration, empty state, header utilities, color/direction conventions for higher-is-better vs. lower-is-better QIs. Per-QI tile labels and tooltips owned by each QI's own outline. | 4 | Casey + Claude
DEC23 | 2026-04-23 | TAT Compliance tile uses a new wrapper endpoint, not /summary directly | Code audit of DIGI-UW/OpenELIS-Global-2 confirms TAT REST API exists (/rest/reports/tat/summary, /detail, /trend, /export) returning mean/median/p90/histogram/breakdown but NOT compliance percentage. Sprint 4 adds a thin /rest/reports/tat/compliance wrapper that applies threshold arithmetic to existing histogram data. No service-layer changes; pure controller addition. Reuses TATReportServiceImpl and TATCalculationService unchanged. | 4 | Casey + Claude (via code audit)
DEC24 | 2026-04-23 | QA Overview is a thin aggregator; no overall status banner | The page composes existing pillar endpoints (with thin wrappers as needed) but owns no analytical logic. Deliberately avoids a single overall 'amber' banner across all pillars because that would conceal which pillar drives the worst signal. Five-question strip + 4 tiles carry the message. | 1 | Casey + Claude
DEC25 | 2026-04-23 | Q4 'Open NCEs?' headline counts Critical severity only | Critical-severity only for the question-strip headline; the QMS pillar tile's secondary line shows total open NCEs. Avoids a flood of minor NCEs painting the strip red. | 1 | Casey + Claude
DEC26 | 2026-04-23 | QA Overview pillar endpoint audit — QC + EQA need wrappers, NCE uses existing | Code audit of DIGI-UW/OpenELIS-Global-2 confirms: (a) QC has /rest/qc/dashboard/summary with months window but lacks section breakdown — Sprint 1 adds /rest/qc/dashboard/sections (~2-3h); (b) EQA has /rest/eqa/orders/summary by status only, lacks scheme/cycle rollup — Sprint 1 adds /rest/eqa/cycles/latest-performance (~2-3h); (c) NCE has full /rest/nce/dashboard returning all needed fields — use directly with client filter in v1, server summary deferred. Wrappers follow same flag-and-proceed pattern as TAT compliance. | 1 | Casey + Claude (via code audit)
DEC27 | 2026-04-23 | EQA tile 'last completed cycle' = most recent GRADED cycle | Cycles whose submission deadline has passed but the provider hasn't graded yet are skipped. Tile reflects actual performance, not in-flight participation. Stable result; doesn't flip until next graded cycle lands. | 1 | Casey
DEC28 | 2026-04-23 | Multi-scheme EQA rollup = worst-of across schemes' latest graded cycles | Lab enrolled in N schemes: find most-recent-graded-cycle per scheme, take worst status across them. Tile primary status = worst scheme; secondary line names the offender (e.g., 'microbiology last cycle: 2 fails'). | 1 | Casey
DEC29 | 2026-04-23 | EQA cycles wrapper deferred from Sprint 1 to Sprint 5 (pending EQA V2 build) | EQA V2 is specced but not yet built. The cycle/scheme model the latest-performance wrapper queries arrives with V2 in Sprint 5. QA Overview EQA tile and Q2 of the five-question strip render gray 'EQA performance data pending — available after EQA V2 ships' from Sprint 1 launch through Sprint 5. Deep-links during the gap point to the existing EQA Orders page. | 1 | Casey | DEC26 (Sprint 1 EQA wrapper)
DEC30 | 2026-04-23 | MVP KPI Rollup ships as Sprint 2 fast-follow; closing FRS in spec sequence | Thin slice of QI Dashboard with three tiles (Rejection Rate, Amendment Rate, TAT Compliance) using only existing data + small wrappers. Same URL as Sprint 4 full dashboard; replaced in place. No QI Configuration page in MVP. No Critical Callback tile (schema-pending). MVP banner explains the user-visible state. Detail placeholders for v1; full detail pages arrive in Sprint 4. | 2-MVP | Casey
DEC31 | 2026-04-23 | TAT compliance wrapper (DEC23) pulled forward to Sprint 2 MVP | Originally specced for Sprint 4 build alongside the full QI Dashboard. MVP needs it earlier. Same wrapper, same controller, same DTO — just earlier sprint placement. No double-build. | 2-MVP | Casey + Claude | DEC23 (Sprint 4 placement)
DEC32 | 2026-04-23 | MVP includes NCE Pulse tile (4 tiles total) | Open critical NCEs + overdue CAPAs as a 4th tile. No new backend; client-side filter on existing /rest/nce/dashboard payload. Tile drill-through goes to NCE Register filtered to critical-open set. ~1h frontend lift; meaningfully completes the four-tile MVP layout. | 2-MVP | Casey
DEC33 | 2026-04-23 | MVP reporting windows: Rolling 7d / 30d / 90d / YTD | Default Rolling 30d. Skip 'This quarter' (less common, deferred to Sprint 4). User-persistence carries across the MVP→full swap. | 2-MVP | Casey
DEC34 | 2026-04-23 | MVP banner deleted cleanly when Sprint 4 ships | No graduated banner, no first-visit toast, no leftover MVP signage. Smallest user-visible change at swap; users just notice the dashboard got more capable. | 4 | Casey
DEC35 | 2026-04-23 | CAPA Register is read-mostly; authoring stays on NCE detail | Bulk reassign and bulk mark-complete are the only edit actions; full CAPA authoring + per-CAPA effectiveness review entry remain on the NCE detail page (per NCE Report FRS v3.1 §8). Avoids duplicate forms. | 3 | Casey + Claude
DEC36 | 2026-04-23 | Electronic Signature Log excludes login + config-change events | Login = session events (not signatures). Config-change events route to Audit Trail, not E-Sig Log. Keeps the log signal-dense for inspectors. | 3 | Casey + Claude
DEC37 | 2026-04-23 | Accreditation Status v1 ships with ISO 15189:2022 + CAP COM + CAP GEN bundled | Three standards in v1, configurable enable/disable per lab. Other standards (ISO 17025, country-specific) deferred to v2 — page architecture supports adding via configuration without code changes. | 3 | Casey
DEC38 | 2026-04-23 | Accreditation Status default v1 CAP mapping is a curated subset, not full checklist | CAP COM and GEN have 200+ items each. v1 default mapping covers ~50 cleanest-mapping items per checklist; rest marked 'manual evidence needed' until lab configures them. Avoids shipping a config burden that drives the page status amber on first use. | 3 | Casey + Claude
DEC39 | 2026-04-23 | Accreditation Status: 'manage' role cannot override Outstanding to Met without evidence | The whole point of the page is that the system tracks evidence honestly. Off-system evidence requires a manual evidence record attached. Lab-configurable override deferred to v2 if customers ask. | 3 | Casey + Claude
DEC40 | 2026-04-23 | CAPA Register: orphaned-by-recurrence CAPAs stay with original NCE | When a parent NCE moves to closed_recurrence (effectiveness review = Not Effective spawns a linked NCE), the original CAPAs stay linked to the original NCE. The new recurrence-linked NCE gets its own freshly-authored CAPAs. Original parent NCE column shows a 'Linked-recurrence' badge so the register surfaces the relationship without conflating two correction attempts. | 3 | Casey
DEC41 | 2026-04-23 | E-Sig Log: bulk attestation = N rows, one per artifact | Batch-acknowledging N NCEs in one click produces N rows in the log, not 1 aggregated row. Every signature is its own attested event for inspection purposes; reason text repeats fine. Inspector reads the log row by row and sees each acknowledged artifact independently. | 3 | Casey
DEC42 | 2026-04-23 | CAPA Register: 'Completed (last 90 days)' tile fixed at 90d v1; configurable v2 | Aligns with quarterly QA review cadence at most clinical labs. Configurability deferred to v2 if customers ask for 30d / 365d windows. | 3 | Casey
DEC43 | 2026-04-23 | CAPA Register: add Pending Effectiveness Review tile + filter (in addition to NCE Dashboard) | Effectiveness review work surfaced both on NCE Dashboard's Pending Verification view AND CAPA Register's new tile/filter. QA Officers who live in the CAPA Register get a top-level signal without context-switching. Joins via parent NCE's nce_effectiveness_review state. | 3 | Casey
DEC44 | 2026-04-23 | CAPA Register: Bulk Mark-Complete uses single shared resolution note v1 | Warning banner: 'This note applies to all {N} selected CAPAs.' Per-CAPA notes deferred to v2 if labs ask. Fast common case for shared-action completions (single training session satisfies multiple CAPAs). | 3 | Casey
DEC45 | 2026-04-23 | E-Sig Log: 4 audit tables don't exist; use unified electronic_signature table | Code audit revealed result_history, nce_audit_log, sample_audit_log, qc_audit_log all MISSING. Instead, OpenELIS already has org.openelisglobal.esig.valueholder.ElectronicSignature with record_type discriminator + signer_id + signed_at + client_ip + user_agent + signature_meaning + rejection_reason. Single-table read replaces UNION ALL. Endpoint effort drops from ~6-8h to ~2-3h. Resolves B1 + B2 in one finding. Optional small migration adds prior_state/new_state columns to electronic_signature for state-change tracking on the row expansion. | 3 | Casey + Claude (via code audit) | DEC36-style scope (4-table union)
DEC46 | 2026-04-23 | E-Sig Log: API-driven signatures show as 'API client (via API)' | Signer field shows the calling system's identity (e.g., 'EHR-INTEGRATION (via API)'). Reason captured from API payload. Inspectable as machine-driven. Worth flagging for v2 once a first partner integration surfaces the case; out of v1 MVP scope. | 3 | Casey
DEC47 | 2026-04-23 | E-Sig Log: unlimited retention v1; configurable v2 | Default = never delete. Configurable retention policy (GDPR right-to-erasure, regulatory minimums) deferred to v2. Storage is cheap; deleting signed-record evidence is risky. | 3 | Casey
DEC48 | 2026-04-23 | Accreditation Status — REDIRECTED to lab-attested registry model | Major reframing. The earlier draft modeled this page as a clause-by-clause evidence rollup with default ISO 15189 + CAP COM/GEN mappings, evidence-stale logic, and Outstanding/Met/N-A states. The new model is a self-attestation registry: lab declares which accreditations it holds (standard, body, awarded date, expires date, scope, optional certificate document, internal notes). System tracks date-driven status (Current / Expiring soon / Inspection overdue / Expired). A separate 'QA evidence at a glance' section provides drill-through tiles to existing QA surfaces but is NOT mapped to specific clauses. Easier to manage in incomplete-information state; easier to ship; matches how labs talk about their accreditation. Endpoint effort drops from ~12-16h to ~6-8h. Single new accreditation_record table; one small internal_audit_review_log table. Collapses C1-C6 entirely. | 3 | Casey | DEC37 (3 standards bundled), DEC38 (CAP starter subset), DEC39 (no override without evidence)

## Deferred to v2+
ID | Item | Why Deferred | Target | Dependencies
V01 | QC Lot Management (target/SD governance) | Out of v1 scope; current QC works without formal lot governance. | v2 — Sprint 7+ | Statistical QC pillar live.
V02 | Accreditation Binder export (PDF) | Large build; single-site rollup view sufficient for v1. | v2 — Sprint 8+ | Accreditation Status rollup shipped (Sprint 3).
V03 | Time-boxable Inspector/Auditor credentials | Flexible-roles engine enhancement, not a role definition. | v2 | Flexible-roles engine shipped; bundle recipe documented.
V04 | Multi-site / multi-lab rollup dashboards | Separate initiative for ministry networks. | v2+ | Single-site v1 stable.
V05 | Document Control module (ISO 15189 §8.3) | QMS pillar stub in v1; full module later. | v2+ | QMS pillar live.
V06 | Equipment Management module (§6.4) | Adjacent to QMS; separate module. | v2+ | —
V07 | Risk Register (§8.5) | QMS expansion. | v2+ | QMS pillar live.
V08 | Internal Audit Tracker (§8.9) | QMS expansion. | v2+ | QMS pillar live.